## Slide 1: Sirona recovery Access Point NIATx Team
Kim Stangel: kstangel@sironarecovery.org
Meghan Wautier mwautier@sironarecovery.org
Chris Honecker chonecker@sironarecovery.org
Carly Klein cklein@sironarecovery.org
Alex Drew adrew@sironarecovery.org
Satisfaction Guaranteed!

## Slide 2: Project AIM & Impact
Satisfaction Guaranteed
The AIM for this project is to meet or exceed a 90 percent rate of distributing satisfaction surveys to consumers following completion of their CARS assessments.
Expected impact is to (1) have an accurate measure to observe overall client satisfaction, and (2) obtain a basis for areas the Access Point program can make future improvements.
Target Population: This project focused on Milwaukee County consumers aged 18-59 referred to the Sirona Recovery Access Point program.

## Slide 3: Strategies & PDSA Cycles
PDSA Cycle 1: The Procedural checklist when completing an Access Point assessment will include a step for distributing a survey to the consumer.
PDSA Cycle 2: Access Point staff will acknowledge whether a satisfaction survey was distributed to the client, and in what method (text, fax, hard copy, email, etc.). This will be included in the Data Points sent to Meghan Wautier following each assessment.

## Slide 4: Project Results
Project length was six months: April – September 2021
A total of 126 assessments were completed.
106 participants were distributed surveys via text, in-person, email, and fax. 13 clients were assessed in custody without reliable way to provide the survey without influencing results by staff presence. 4 clients declined to participate in the survey. 3 clients were not distributed surveys due to AP Intake Specialist error.
Percentage of total distributed surveys among the consumers during this trial period resulted in 84%.

## Slide 5: Moving forward
  Target sustainment measure is 90 percent.
  We will be adopting the acknowledgement of sending the survey as a part of the AP Assessment Checklist.
  We will be continuing to list the method of survey distribution when sending data points to a supervisor.
  We are hopeful to utilize information from the surveys to make future program improvements!
Chart: 
| Surveys Given | In-custody Clients | Declined to participate | Staff error
Percent | 84 | 10 | 3.5 | 2.5