## Slide 1: Enhancing Transitions for Consumers (etc.)
Jewish Family Services
Kevin Boland, Director of Social Services
Sam Kovatch, CCS Administrator
Shelby Guendel, Community Programs Coordinator
Tina Staszak, CCS Clinical Manager
Sadie Wolfe and Q Hicks, UWM Social Work Interns
Notes: Kevin Boland, Director of Social Services – Executive Sponsor
Sam Kovatch– Change Leader and helped with the transition process development and implementation
Change Team - Shelby Guendel - supervised interns, oversaw survey implementation, and data analysis
Change Team - Tina Staszak - helped with transition process development and implementation
Change Team - UWM Social Work Interns on internship in Spring 2022 helped with survey implementation and data analysis

## Slide 2: Project AIM and Impact
  AIM:
  Increase CCS consumer satisfaction in transition process from baseline of 69% to goal of 80% by April 2023.
  Expected Impact:
  Expected impact is to provide 1) higher levels of CCS consumer satisfaction in transitioning to a new CCS Care Coordinator and 2) provide a detailed process for CCS staff for transitions.

## Slide 3: CHANGE
CCS Satisfaction Survey
  When asked about strengths and areas of improvements of Care Coordinators data showed that transition to a new Care Coordinator was impacting ability to answer question:
    “People keep quitting and say they will stay and don’t”
    “I don’t know because I haven’t had her for long”
    “I don’t know anything yet because I just started with him”
    “New to me-don’t know him well”
Development of Transition Process
Notes: CCS Satisfaction Survey
From March 1, 2022 to April 15, 2022, UWM interns conducted CCS satisfaction surveys to 30 (37%) of current CCS consumers.
When asked about strengths and areas of improvements of Care Coordinators data showed that transition to a new Care Coordinator was impacting ability to answer question:
    “People keep quitting and say they will stay and don’t”
    “I don’t know because I haven’t had her for long”
    “I don’t know anything yet because I just started with him”
    “New to me-don’t know him well”
Knowing that clients are impacted by transitions in Care Coordinators and that Care Coordinators tend to have a higher turnover rate, we wanted to increase satisfaction in the transition process knowing it’s inevitable, which is led to the development of a formal transition process.
The transition process includes a pre-survey and 6 week post survey for the transfer of a consumer to a new Care Coordinator when notice is given and the transfer of a consumer to a new Care Coordinator when no notice is given.
PSDA Cycle 2 – Development of Transition Process and Data Collection
Transition process was developed including for the transfer of a consumer to a new Care Coordinator when notice is given, the transfer of a consumer to a new Care Coordinator when no notice is given, and a 6-week follow up survey after the transfer.
This initial survey is now our baseline for consumer satisfaction in the transition process.

## Slide 4: Data
Chart: 
| Very Satisfied | Satisfied | Neither Satisfied Nor Dissatisfied | Dissatisfied | Very Dissatisfied
Satisfaction Ratings (in percent) | 0.692 | 0.154 | 0.154 | 0 | 0
Notes:   69.2% reported that they were very satisfied with transition process at 6 week follow up
  15.4% reported that they were satisfied with transition process at 6 week follow up
  15.4% reported that they were neither satisfied nor dissatisfied with transition process at 6 week follow up
  0% reported that they were dissatisfied with transition process at 6 week follow up
  0% reported that they were very dissatisfied with transition process at 6 week follow up
The Pre-and post survey is now our baseline data for consumer satisfaction in the transition process. Because what we are measuring depends on the retaining of Care Coordinators, our data collection will need to continue from now through April 2023 to ensure an adequate sample size.
***ADD IN GRAPHS

## Slide 5: Adopt
Although we are still in the data collection phase, we will continue to adopt the pre-post survey for transition process to measure our aim.
Utilize the information from the surveys to make future program improvements.